## 2018-2019
Task | Primary | Other 1 | Other 2 | Timeframe | 2018 | 2019
Spring Meeting Timeline
Send "Hold the Date" e-mail blast for Spring Meeting including reminder on poster session | President | Administrator | Poster Chair | 30 days (1 month) after Fall meeting | 2018-10-22 | 2019-10-21
Election slate sent to President for BOD review | Nominating Chair | President | BOD Chair | 112 days (16 weeks) before Spring meeting | 2017-12-30 | 2018-11-24
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Spring meeting | 2017-12-30 | 2018-11-24
Prepare materials for distribution: Cover letter Registration form link Agenda Poster session information Membership activities | Membership Chair Program Chair | Poster Chair | President Administrator | 112 days (16 weeks) before Spring meeting | 2017-12-30 | 2018-11-24
Send e-mail blast reminder Focus: Hotel Arrangements | Arrangements Chair | Administrator | President | 98 days (14 weeks) before Spring meeting | 2018-01-13 | 2018-12-08
Send e-mail blast reminder Focus: Poster Session Call for Abstracts | Poster Chair | Administrator |  | 70 days (10 weeks) before Spring meeting | 2018-02-10 | 2019-01-05
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 63 days (9 weeks) before Spring meeting | 2018-02-17 | 2019-01-12
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Spring meeting | 2018-02-24 | 2019-01-19
Send e-mail blast reminder Focus: Plenary speakers | Program Chair | Administrator | President | 56 days (8 weeks) before Spring meeting | 2018-02-24 | 2019-01-19
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Spring meeting | 2018-02-24 | 2019-01-19
Send Election Ballot | Nominating Chair | Administrator | President | 56 days (8 weeks) before Spring meeting | 2018-02-24 | 2019-01-19
Send e-mail blast reminder Focus: Forum Sessions | Forum Chair | Administrator | President | 49 days (7 weeks) before Spring meeting | 2018-03-03 | 2019-01-26
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 42 days (6 weeks) before Spring meeting | 2018-03-10 | 2019-02-02
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Spring meeting | 2018-03-10 | 2019-02-02
Send Election Ballot reminder | Nominating Chair | Administrator | President | 42 days (6 weeks) before Spring meeting | 2018-03-10 | 2019-02-02
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Directors |  | 35 days (5 weeks) before Spring meeting | 2018-03-17 | 2019-02-09
Send e-mail blast reminder Focus: Final Poster Session Call for Abstracts | Poster Chair | Administrator | President | 35 days (5 weeks) before Spring meeting | 2018-03-17 | 2019-02-09
Make tour and networking arrangements | Membership Chair | Administrator |  | 35 days (5 weeks) before Spring meeting | 2018-03-17 | 2019-02-09
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Spring meeting | 2018-03-22 | 2019-02-14
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Spring meeting | 2018-03-24 | 2019-02-16
Send e-mail blast reminder Focus: Networking, Membership Dinners and Location Opportunities | Membership Chair | Administrator | President | 28 days (4 weeks) before Spring meeting | 2018-03-24 | 2019-02-16
Finalize Poster Session Arrangements | Poster Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2018-03-31 | 2019-02-23
Submit final program agenda, speaker bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Spring meeting | 2018-03-31 | 2019-02-23
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Spring meeting | 2018-03-31 | 2019-02-23
Submit committee and officer reports | Committee Chairs Officers | Administrator | President | 21 days (3 weeks) before Spring meeting | 2018-03-31 | 2019-02-23
Send e-mail blast reminder Focus: Mobile App | Mobile Coordinator | Administrator |  | 21 days (3 weeks) before Spring meeting | 2018-03-31 | 2019-02-23
Send e-mail blast reminder Focus: Plenary speakers and Forum sessions | Program Chair Forum Chair | Administrator | President | 14 days (2 weeks) before Spring meeting | 2018-04-07 | 2019-03-02
Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, Mobile | Membership Chair, Social Media Chair, Mobile Coord | Administrator | President | 7 days (1 week) before Spring meeting | 2018-04-14 | 2019-03-09
Spring Meeting Dates |  |  |  |  | 2018-04-21 | 2019-03-16
Fall Meeting Timeline
Send "Hold the Date" e-mail blast for Fall Meeting | President | Administrator |  | 30 days (1 month) after Spring Meeting | 2018-05-21 | 2019-04-15
Finalize PDC brochures Post program on website | Professional Development Chair | Program Chair | Administrator | 112 days (16 weeks) before Fall meeting | 2018-06-02 | 2019-06-01
Prepare materials for distribution: Cover letter Registration form link Agenda Poster session information Membership activities | Membership Chair Program Chair | Poster Chair | President Administrator | 112 days (16 weeks) before Fall meeting | 2018-06-02 | 2019-06-01
Send e-mail blast reminder Focus: Hotel Arrangements | Arrangements Chair | Administrator | President | 98 days (14 weeks) before Fall meeting | 2018-06-16 | 2019-06-15
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit Chair | Administrator | President | 70 days (10 weeks) before Fall meeting | 2018-07-14 | 2019-07-13
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 63 days (9 weeks) before Fall meeting | 2018-07-21 | 2019-07-20
Prepare postcard for mailing | Administrator | President |  | 56 days (8 weeks) before Fall meeting | 2018-07-28 | 2019-07-27
Send e-mail blast reminder Focus: Plenary speakers | Program Chair | Administrator | President | 56 days (8 weeks) before Fall meeting | 2018-07-28 | 2019-07-27
Send Press Release | Outreach Chair | Administrator |  | 56 days (8 weeks) before Fall meeting | 2018-07-28 | 2019-07-27
Send e-mail blast reminder Focus: Webstreaming Option (if available) | Webstreaming Chair | Administrator | President | 49 days (7 weeks) before Fall meeting | 2018-08-04 | 2019-08-03
Send e-mail blast reminder Focus: Professional Development courses | Professional Development Chair | Administrator | President | 42 days (6 weeks) before Fall meeting | 2018-08-11 | 2019-08-10
Communicate PDC Headcounts for decision making on holding all courses | Professional Development Chair |  |  | 42 days (6 weeks) before Fall meeting | 2018-08-11 | 2019-08-10
Decide whether to hold all Professional Development courses | Professional Development Chair | Board of Directors |  | 35 days (5 weeks) before Fall meeting | 2018-08-11 | 2019-08-17
Send e-mail blast reminder Focus: Exhibit and Reception | Exhibit Chair | Administrator | President | 35 days (5 weeks) before Fall meeting | 2018-08-18 | 2019-08-17
Make tour and networking arrangements | Membership Chair | Administrator |  | 35 days (5 weeks) before Fall meeting | 2018-08-18 | 2019-08-17
Send AV requirements for plenary sessions and PD courses to Arrangements Chair | Program Chair | Professional Development Chair |  | 30 days before Fall meeting | 2018-08-23 | 2019-08-22
Prepare timeline for Fall Meeting Send to Administrator | President | Administrator |  | 28 days (4 weeks) before Fall meeting | 2018-08-25 | 2019-08-24
Send e-mail blast reminder Focus: Networking, Membership Dinners and D.C. Opportunities | Membership Chair | Administrator | President | 28 days (4 weeks) before Fall meeting | 2018-08-25 | 2019-08-24
Finalize Exhibit Arrangements | Exhibit Chair | Administrator | Arrangements Chair | 28 days (4 weeks) before Fall meeting | 2018-08-25 | 2019-08-24
Submit final program agenda, bios, and presentation handouts | Program Chair | Administrator |  | 21 days (3 weeks) before Fall meeting | 2018-09-01 | 2019-08-31
Submit professional development course materials | Professional Development Chair | Instructors | Administrator | 21 days (3 weeks) before Fall meeting | 2018-09-01 | 2019-08-31
Submit committee and officer reports | Committee Chairs Officers | Administrator |  | 21 days (3 weeks) before Fall meeting | 2018-09-01 | 2019-08-31
Send e-mail blast reminder Focus: Mobile App | Mobile Coordinator | Administrator |  | 21 days (3 weeks) before Fall meeting | 2018-09-01 | 2019-08-31
Send e-mail blast reminder Focus: Program and Webstreaming | Program Chair Webstreaming Chair | Administrator | President | 14 days (2 weeks) before Fall meeting | 2018-09-08 | 2019-09-07
Review Nominating Committee membership and fill vacancies as needed | President | Nominating Chair |  | 14 days (2 weeks) before Fall meeting | 2018-09-08 | 2019-09-07
Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, Mobile | Membership Chair, Social Media Chair, Mobile Coord | Administrator | President | 7 days before Fall meeting | 2018-09-15 | 2019-09-14
Fall Meeting Dates |  |  |  |  | 2018-09-22 | 2019-09-21
Membership Year End Timeline
[5 empty] | 2018 | 2019
Send membership reminder | Web Committee | Membership Chair | Administrator | 90 days before membership expiration | 2018-10-02 | 2019-10-02
Send membership reminder | Web Committee | Membership Chair | Administrator | 60 days before membership expiration | 2018-11-01 | 2019-11-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 30 days before membership expiration | 2018-12-01 | 2019-12-01
Send membership reminder | Web Committee | Membership Chair | Administrator | 15 days before membership expiration | 2018-12-16 | 2019-12-16
Send membership reminder | Web Committee | Membership Chair | Administrator | 7 days before membership expiration | 2018-12-24 | 2019-12-24
Send membership reminder | Web Committee | Membership Chair | Administrator | December 31 of current year | 2018-12-31 | 2019-12-31
[5 empty] | 2018-12-31 | 2019-12-31