## Timeline-2025
Category | Task | Accountable | Responsible | Consulted | Informed | Parties involved | Timeframe | 2025 | Revised Februay 2025
Annual Meeting Timeline | Cancellation (25% lost room profit) | Arrangements Liaison | Arrangements Chair | Board | Board | Arrangements Liaison, Arrangements Chair, Board, Board | 360 days prior to meeting ¦ determined by hotel contract | 2024-09-19 | HARD DATE
Annual Meeting Timeline | Prepare timeline for Annual Meeting | President | President | Officers | Board | President, President, Officers, Board |  | 2024-12-31 | for following year's meeting Hard date
Annual Meeting Timeline | Send "Hold the Date" e-mail blast for Annual Meeting combined with Membership Renewal | President | Administrator | Officers | Board | President, Administrator, Officers, Board | Following Annual Meeting | 2025-02-01 | hard date
Annual Meeting Timeline | Send Call for Program Abstracts - Abstracts Due April 5 | Program Committee Liaison | Program Committee Chair with support from Administrator | Program Committee | Board | Program Committee Liaison, Program Committee Chair with support from Administrator, Program Committee, Board |  | 2025-02-01 | hard date
Annual Meeting Timeline | Review registration rate for Annual Meeting | Treasurer | Treasurer/Finance Committee | Board |  | Treasurer, Treasurer/Finance Committee, Board, |  | 2025-02-01
Annual Meeting Timeline | Prepare exhibitor and sponsorship forms | Exhibits Liaison; Arrangements Liaison | Exhibits Chair | Exhibits Committee | Board | Exhibits Liaison, Exhibits Chair, Exhibits Committee, Board, Arrangements Liaison |  | 2025-02-20
Annual Meeting Timeline | Send exhibitor and sponsorship email blast with link to forms | Exhibits Liaison | Exhibits Chair with support from Administrator | Exhibits Committee | Board | Exhibits Liaison, Exhibits Chair with support from Administrator, Exhibits Committee, Board |  | 2025-02-28
Annual Meeting Timeline | Send REMINDERS - Call for Program Abstracts - Abstracts Due April 5 | Program Committee Liaison | Program Committee Chair with support from Administrator | Program Committee | Board | Program Committee Liaison, Program Committee Chair with support from Administrator, Program Committee, Board |  | 2025-03-01 | hard date
Annual Meeting Timeline | Revise registration rates for Annual Meeting | President | Treasurer/Finance Committee | Board | Membership | President, Treasurer/Finance Committee, Board, Membership |  | 2025-03-01 | HARD DATE for President or Treasurer to make motion to Board
Annual Meeting Timeline | Cancellation (40% lost room profit) | Arrangements Liaison | Arrangements Chair | Board | Board | Arrangements Liaison, Arrangements Chair, Board, Board | 359 to 180 days prior to meeting ¦ determined by hotel contract | 2025-03-19 | HARD DATE
Annual Meeting Timeline | Send Call for Poster Abstracts - deadline to submit is below (must allow time to review and then allow individuals to register at early bird rate and get in before hotel cut-off) | Poster Committee Liaison | Poster Committee Chair with support from Administrator | Poster Committee | Board | Poster Committee Liaison, Poster Committee Chair with support from Administrator, Poster Committee, Board | 168 days (6 months) before meeting | 2025-04-05 | make sure deadline to submit accommodates time to review/accept and still register at the early bird rate
Annual Meeting Timeline | Finalize PDC brochures Post program on website | PDC Liaison | PDC Chair with support from Administrator | PDC | Board | PDC Liaison, PDC Chair with support from Administrator, PDC, Board | 168 days (6 months) before meeting | 2025-04-05
Annual Meeting Timeline | Prepare materials for distribution: Registration form link Agenda Poster session information Membership activities Include link to share LinkedIn post in confirmation email of registration | President | Administrator | Program, Poster, Member Engagement, Arrangements Committees | Board | President, Administrator, Program, Poster, Member Engagement, Arrangements Committees, Board | 168 days (6 months) before meeting | 2025-04-05
Annual Meeting Timeline | Send details to Chemical Watch (Media Sponsor), CHCS, AIHA and other alliances for distribution of meeting information | Alliance Chair | Alliance Chair with support from Administrator | Officers | Board | Alliance Chair, Alliance Chair with support from Administrator, Officers, Board | 168 days (6 months) before meeting | 2025-04-05
Annual Meeting Timeline | Open registration | Administrator | Administrator | Board | Board | Administrator, Board | 4 months before meeting | 2025-05-01
Annual Meeting Timeline | Early Bird Registration Deadline email blast | President | Administrator | Officers | Board | President, Administrator, Officers, Board | 56 days (8 weeks) before meeting | 2025-06-01
Annual Meeting Timeline | Send e-mail blast reminder Focus: Professional Development courses | PDC Liaison | PDC Chair with support from Administrator | PDC Committee | Board | PDC Liaison, PDC Chair with support from Administrator, PDC Committee, Board | 98 days (14 weeks) before meeting | 2025-06-14
Annual Meeting Timeline | Early Bird registration Deadline | Administrator | Administrator | Officers | EVERYONE |  |  | 2025-06-15 | HARD DATE
Annual Meeting Timeline | Finalize Awards to be presented - PDC Awards | PDC Liaison | PDC Chair with support from Administrator | PDC Chair with support from Administrator | Board | Member Engagement Liaison, Member Engagement Chair, Member Engagement Committee, Board | 82 days (10 weeks) before meeting | 2025-06-30
Annual Meeting Timeline | Finalize Awards to be presented - Lifetime Achievement, Outstanding Service, Outstanding Volunteers | Nominating committee Liaison | Nominating Chair | Nominating Committee | Board | Nominating committee Liaison, Nominating Chair, Nominating Committee, Board | 82 days (10 weeks) before meeting | 2025-06-30
Annual Meeting Timeline | Send e-mail blast reminder FOCUS: registration deadline | Administrator | Administrator | Officers | Board | Administrator, Administrator, Officers, Board | 63 days (9 weeks) before meeting | 2025-07-01
Annual Meeting Timeline | Deadline to submit Poster Abstracts | Poster Committee Liaison | Poster Committee Chair with support from Administrator | Poster Committee | Board | Poster Committee Liaison, Poster Committee Chair with support from Administrator, Poster Committee, Board |  | 2025-07-12 | make sure deadline to submit accommodates time to review/accept and still register at the early bird rate
Annual Meeting Timeline | Send e-mail blast reminder Focus: Exhibit/Poster/Reception | Administrator | Administrator | Exhibit, Poster, Arrangements Committees | President | Administrator, Administrator, Exhibit, Poster, Arrangements Committees, President | 70 days (10 weeks) before meeting | 2025-07-12
Annual Meeting Timeline | Send Exhibits requirements to hotel | Arrangements Liaison | Arrangements Chair | Exhibits Committee | Board | Arrangements Liaison, Arrangements Chair, Exhibits Liaison, Exhibits Chair | determined by hotel contract | 2025-07-15 | HARD DATE
Annual Meeting Timeline | Cancellation (60% lost room profit) | Arrangements Liaison | Arrangements Chair | Board | Board | Arrangements Liaison, Arrangements Chair, Board, Board | determined by hotel contract | 2025-07-19 | HARD DATE
Annual Meeting Timeline | Send e-mail blast reminder Focus: Hotel Arrangements | Administrator | Administrator | Arrangements Committee | President | Administrator, Arrangements Committee, President | 63 days (9 weeks) before meeting | 2025-07-19
Annual Meeting Timeline | Inform presenters their posters have been accepted | Posters Liaison | Poster Committee Chair | Poster Committee | Board | Posters Liaison, Poster Committee Chair, Poster Committee, Board |  | 2025-07-22 | HARD DATE
Annual Meeting Timeline | Send e-mail blast reminder Focus: Plenary speakers | Administrator | Administrator | Program Committee | President | Administrator, Administrator, Program Committee, President | 56 days (8 weeks) before meeting | 2025-07-26
Annual Meeting Timeline | Communicate PDC Headcounts to Board for decision making on holding all courses | PDC Liaison | PDC Chair | PDC Committee | Board | PDC Liaison, PDC Chair , PDC Committee, Board | 56 days (8 weeks) before meeting | 2025-07-26
Annual Meeting Timeline | Send Email to PDC Awardees | PDC Liaison | PDC Chair | PDC | Administrator | PDC Liaison, PDC Chair, PDC, Administrator | 56 days (8 weeks) before meeting | 2025-07-26
Annual Meeting Timeline | Decide whether to hold all Professional Development courses | PDC Liaison | PDC Chair | PDC Committee | Board | PDC Liaison, PDC Chair, PDC Committee, Board | 49 days (7 weeks) before meeting | 2025-08-02
Annual Meeting Timeline | Send e-mail blast reminder Focus: Exhibit/Poster/Reception | Administrator | Administrator | Exhibit, Poster, Arrangements Committees | President | Administrator, Administrator, Exhibit, Poster, Arrangements Committees, President | 35 days (5 weeks) before meeting | 2025-08-16
Annual Meeting Timeline | Finalize tour and networking arrangements | Member Engagement Liaison | Member Engagement Chair | Member Engagement Committee | Board | Member Engagement Liaison, Member Engagement Chair, Member Engagement Committee, Board | 35 days (5 weeks) before meeting | 2025-08-16
Annual Meeting Timeline | Submit professional development course materials | PDC Liaison | PDC Chair | PDC | Board | PDC Liaison, PDC Chair, PDC, Board | 35 days (5 weeks) before meeting | 2025-08-16 | Hard Deadline - suggest that SCHC will not be able to support requests that come in after deadline
Annual Meeting Timeline | Send AV requirements for plenary sessions and PD courses to Arrangements | Arrangements Liaison | Arrangements Chair | Professional Development Committee | President | Arrangements Liaison, Arrangements Chair, Professional Development Commitee, President | 30 days before meeting ¦ determine by hotel contract | 2025-08-21 | Hard Deadline - suggest that SCHC will not be able to support requests that come in after deadline
Annual Meeting Timeline | Final registration Deadline - No registration is accepted after this date. | Arrangements Liaison | Administrator | Board | EVERYONE |  |  | 2025-08-22 | HARD DATE - No registration is accepted after this date
Annual Meeting Timeline | Send e-mail blast reminder Focus: Networking, Membership Dinners and travel info | Administrator | Administrator | Member Engagement Committee | President | Administrator, Member Engagement Committee, President | 28 days (4 weeks) before meeting | 2025-08-23
Annual Meeting Timeline | Submit final program agenda, bios, and presentation handouts to Board | Program Committee Liaison | Program Committee Chair | Program Committee | Board | Program Committee Liaison, Program Committee Chair, Program Committee, Board | 28 days (4 weeks) before meeting | 2025-08-23 | Hard Deadline - suggest that SCHC will not be able to support requests that come in after deadline, particularly for handouts
Annual Meeting Timeline | Final Date for Hotel Reservations (after this date rooms no longer held for SCHC) | Arrangements Liaison | Arrangements Chair | EVERYONE | EVERYONE | Arrangements Liaison, Arrangements Chair, EVERYONE | determined by hotel contract | 2025-08-29 | HARD DATE
Annual Meeting Timeline | HOTEL REGISTRATION CUT-OFF DATE - set by hotel | Arrangements Liaison | Arrangements Chair | EVERYONE | EVERYONE | Arrangements Liaison, Arrangements Chair, EVERYONE | determined by hotel contract | 2025-08-29 | HARD DATE set by Hotel
Annual Meeting Timeline | Final written confirmation of banquet services due to hotel. Final headcounts for courses, and meeting are needed prior to ensure written order is complete. | Administrator | Arrangements Chair | Board | Board | Administrator, Arrangements Chair, Board, Board | determined by hotel contract | 2025-08-29 | HARD DEADLINE
Annual Meeting Timeline | Submit committee and officer reports to Board Chair and Administrator | Committee Liaisons | Committee Chairs and Officers |  | Board Chair and Administrator | Committee Liaisons, Committee Chairs and Officers, Board Chair and Administrator | 21 days (3 weeks) before meeting | 2025-08-30
Annual Meeting Timeline | Send e-mail blast reminder Focus: Event Page | Administrator | Administrator |  | President | Administrator, President | 21 days (3 weeks) before meeting | 2025-08-30
Annual Meeting Timeline | Submit exhibit floor plan to DC fire department | Arrangements Liaison | Arrangements Chair | Exhibits & Poster Committees | Board | Arrangements Liaison, Arrangements Chair, Exhibits Liaison, Exhibits Chair, Poster Liaison, Poster Chair | 21 days before meeting - per DC requirements | 2025-08-31 | HARD DATE
Annual Meeting Timeline | Send e-mail blast reminder Focus: Program | Administrator | Administrator | Program Committee | President | Administrator, Program Committee, President | 14 days (2 weeks) before meeting | 2025-09-06
Annual Meeting Timeline | Review Nominating Committee membership and fill vacancies as needed; send call for candidates | Nominating Liaison | Nominating Chair | Nominating Committee | President | Nominating Liaison, Nominating Chair, Nominating Committee, President | 14 days (2 weeks) before meeting | 2025-09-06
Annual Meeting Timeline | Send e-mail blast reminder Focus: Networking Opportunities, Social Media, Awards, App/Events access | Administrator | Administrator | Member Engagement Committee | President | Administrator, Member Engagement Committee, President | 7 days before meeting | 2025-09-13
Annual Meeting Timeline | Send e-mail blast reminder Focus - hotel registration deadline | Administrator | Administrator | Arrangements Committee | President | Administrator, Arrangements Committee, President | One week prior to hotel cut-off date | 2025-09-13
Annual Meeting Timeline | Cancelleation (100% and 50% of contracted F&B minimum) | Arrangements Liaison | Arrangements Chair | Board | Board | Arrangements Liaison, Arrangements Chair, Board, Board | 59 days up until arrival | 2025-09-19 | HARD DATE
Annual Meeting Timeline | 2025 Meeting Dates | [6 empty] | 2025-09-20 | 2025-09-25
Annual Meeting Timeline | Expense Reports Due | Treasurer | PDC and Program Chairs |  | Administrator | Treasurer, PDC and Program Chairs, , Administrator | 30 days after conclusion of meeting | 2025-11-09 | Hard date - after 30 days SCHC reserves the right not to reimburse
Membership and Course Finances Year End Timeline | Review membership rates | Treasurer | Treasurer/Finance Committee | Board and Member Engagement Committee |  | Treasurer, Treasurer/Finance Committee, Board and Member Engagement Committee |  | 2024-08-01 | HARD DATE
Membership and Course Finances Year End Timeline | Revise membership rates | President | Treasurer/Finance Committee | Board | Membership | President, Treasurer/Finance Committee, Board , Membership |  | 2024-10-01 | HARD DATE for President or Treasurer to make motion to Board
Membership and Course Finances Year End Timeline | Send membership renewals | Treasurer | Administrator |  | Board | Treasurer, Administrator, Board | 60 days before membership expiration | 2024-11-01
Membership and Course Finances Year End Timeline | Send membership reminder | Administrator | Administrator |  |  | Administrator, Administrator | 45 days before membership expiration | 2024-11-16
Membership and Course Finances Year End Timeline | Send membership reminder | Administrator | Administrator |  |  | Administrator, Administrator | 30 days before membership expiration | 2024-12-01
Membership and Course Finances Year End Timeline | Send membership reminder | Administrator | Administrator |  |  | Administrator, Administrator | 15 days before membership expiration | 2024-12-16
Membership and Course Finances Year End Timeline | Dues Expiration | [6 empty] | 2024-12-31
Membership and Course Finances Year End Timeline | Send reminder - membership has lapsed | Administrator |  |  | Board and Committee Chairs | Administrator, Board and Committee Chairs | 15 days after membership expiration | 2025-01-15
Membership and Course Finances Year End Timeline | Send reminder - membership has lapsed | Administrator |  |  | Board and Committee Chairs | Administrator, Board and Committee Chairs | 30 days after membership expiration | 2025-01-30
Membership and Course Finances Year End Timeline | Review PDC rates | PDC Chair | PDC |  |  | PDC Chair, PDC | first quarter of calendar year | 2025-02-28 | HARD DATE
Membership and Course Finances Year End Timeline | Revise PDC rates | Board | PDC Chair | PDC | Board | Board, PDC Chair, PDC, Board | first quarter of calendar year | 2025-02-28 | HARD DATE
2025 Election Events | Election slate sent to President for BOD review Even Years includes Officers | Nominating Liaison | Nominating Chair | President | Board Chair | Nominating Liaison, Nominating Chair, President, Board Chair | Dec. Board Meeting | 2024-12-19 | hard date
2025 Election Events | Notice of election ballot | President | President | Board | Nominating Chair | President, Board, Nominating Chair |  | 2024-12-19 | hard date
2025 Election Events | Announce Upcoming Election | Administrator | Administrator |  | President and Nominating Chair | Administrator, President and Nominating Chair | May | 2025-05-01
2025 Election Events | Meet the Candidate Forum | President | Nominating Chair & Administrator | Member Engagement Committee | Board | President, Nominating Chair & Administrator, Member Engagement Committee, Board | June | 2025-06-01
2025 Election Events | Send Election Ballot - Election deadline is the last day of July | Nominating Liaison | Administrator |  | President | Nominating Liaison, Administrator, President | Approx. 8 weeks before Sept. 1 Term | 2025-07-01 | hard date
2025 Election Events | Send Election Ballot reminder #1 | Administrator | Administrator |  | President and Nominating Chair | Administrator, President and Nominating Chair |  | 2025-07-15
2025 Election Events | Send Election Ballot reminder #2 | Administrator | Administrator |  | President and Nominating Chair | Administrator, President and Nominating Chair |  | 2025-07-30
2025 Election Events | New Term Starts | [6 empty] | 2025-09-01